## Slide 1: Trial Closeout and Reporting
Dawit A. Ejigu (MD, MSc)
Associate Professor,
Department of Pharmacology
SPHMMC

## Slide 2: Outline
Data Management Aspects
Investigational Product Related Aspects
Participants Related Aspects
Reporting Aspects

## Slide 3: Data Management Aspects: Queries closed before closing a trial
Sites need to respond to discrepancies with no delays
Delays lead to memory bias, overburden during trial closure
Data Clarification Forms signed by the investigator
After making changes in EDC need to sign electronically

## Slide 4: Data Management Aspects: Signatures
Sites need to respond to discrepancies with no delays
Delays lead to memory bias, overburden during trial closure
Data Clarification Forms signed by the investigator
After making changes in EDC need to sign electronically

## Slide 5: Data Management Aspects: Reconciliation of Files
ISF vs TMF
Safety reconciliation
Reconciliation of other files

## Slide 6: Data Management Aspects…
PDF of eCRF screens are complete and filed at the investigations sites or designated sites
Contemporary copy
Before submission to the sponsor
Necessary arrangements for data archival
Done by the sites or delegated sites

## Slide 7: Investigational Product Related Aspects
Clinical trial supplies returned or destroyed on site
  Proper accountability
  Instruction to destruction by the sponsor
  Different requirements by RAs
    In the presence of the RA officer
    Sometimes the RA will do the IP destruction

## Slide 8: Participants Related Aspects
Post-trial benefits considered even during planning stage
  Access to the products at a fair price
  In collaboration with donors
  Way of ensuring justice in the trial
  Study result revealed to the participants/the community
  Capacity building activities in consultation with community

## Slide 9: Reporting Aspects
Competent authorities informed about the trial closure
  May need to file confirmation from the authorities
Clinical Study Reports also required by the RAs
  Need to check with the specific RAs

## Slide 10: Reporting Aspects…
Strict timeline for result disclosure after data collection
  12 months after last primary data collection (FDA)
  12 months after last subject last visit (Malaria Vaccine Technology Roadmap)
  “Time to database lock” crucial in selecting sites for clinical trials

## Slide 11
Thank You !