## Slide 1: Financial Management & Strategic Grant Budgeting
Mirkuzie Woldie (MD, MPH)
Professor of Health Systems Management

## Slide 2
By the end of this session, you will be able to:
Calculate full study costs
Build a complete cost picture covering every resource a study truly needs.
Differentiate direct vs. indirect costs
Classify costs correctly and apply the right indirect cost rate.
Address cost-sharing requirements
Identify, document, and value cash and in-kind contributions.
Ensure 100% activity-budget alignment
Guarantee every technical activity is fully funded — and every dollar is justified.
2

## Slide 3: Six building blocks of a defensible grant budget
What counts as the 'full cost' of a study/a program
Direct costs: definitions and examples
Indirect costs and cost-rate agreements
Cost-sharing: cash vs. in-kind, and its risks
The 100% alignment rule — activities to budget lines
Practical demonstration: building a budget from a workplan

## Slide 4
What counts as the true cost of a research study/a program?
A budget built only on activity costs under-recovers every time. Full cost includes everything the institution spends to deliver — and sustain — the study.
Direct Costs
Traceable to this study
+
Indirect Costs
Shared organizational overhead
+
Cost Share
Contributions beyond the grant
=
Full Study
Cost
Rule of thumb: if a resource is consumed to deliver results, it belongs in the cost calculation — whether or not the donor pays for all of it.
Under-costing
Erodes reserves; forces staff to subsidize the grant
Over-costing
Weakens competitiveness; risks donor pushback
Right-costing
Protects sustainability and passes audit
4

## Slide 5: Direct costs: expenses you can point to a single study or program
Costs that are specifically identifiable, easily traced, and incurred for the benefit of this study or program alone.
  Research personnel & fringe
    PI, co-investigator, research assistant, and enumerator time charged to the study
  Travel
    Site visits, data collection travel, and conference dissemination
  Equipment & supplies
    Tablets/ODK licenses, lab and medical supplies, software, and survey tools
  Subawards & participant costs
    Partner-site subawards, IRB fees, and participant incentives

## Slide 6: Indirect costs: the shared cost of keeping the institution running
Facilities
Lab & office space, utilities, maintenance
Shared systems
IT, data security, research software licenses
Research administration
Grant management, finance, HR support
Governance
IRB oversight, institutional leadership

## Slide 7: How to decide indirect costs
Reviewing funder rules
Check the grant guidelines for a strict maximum rate limit.
Look for rules that ban certain costs from being charged as indirect.
See if the funder requires a specific cost allocation plan.
Calculating your actual overhead rate

## Slide 8: Side by side: how the two categories differ
 | Direct costs | Indirect costs
Definition | Expenses tied directly to a specific project. | Expenses shared across the whole organization.
Tracebility | Easily tracked to a single grant activity. | Difficult to link to one specific project.
Purpose | Running the actual project day-to-day. | Supporting the infrastructure of the organization.
Examples | Project staff salaries, travel, field supplies. | Rent, utilities, accounting staff, legal fees.
Budgeting | Itemized line by line in the budget proposal. | Calculated as a percentage of direct costs.

## Slide 9
Cost-sharing: what the institution contributes beyond the grant
Cash Match
•
Cash contributed by the university, a research partner, or a co-funder
•
Recorded like any other study or program expense
•
Must meet the same eligibility rules as grant funds
In-Kind Match
•
Donated faculty time, use of lab space, and in-country partner staff time
•
Valued at fair market rate — not estimated loosely
•
Requires signed effort/donation records as evidence
Watch for: over-committing cost-share you can't document, valuing in-kind at inflated rates, or counting the same contribution toward two different grants.
8

## Slide 10
Worked example: a 20% mandatory cost-share on a global health award
Chart: Study Financing Structure ($500,000 Total)
| Donor Grant Funds | Cash Match | In-Kind Match | Total Cost-Share
USD | 400000 | 60000 | 40000 | 100000
Grant request: $400,000 (80% of total study cost)
Required cost-share: $100,000 (20%), split cash + in-kind
Every cost-share dollar must be traceable to a source and a value
Under-delivering committed cost-share can trigger funds recovery
9

## Slide 11
Conduct baseline household survey (500 respondents, 5 districts)
Enumerator salaries, tablets/ODK licenses, transport
Interview 40 health facility managers on service delivery
Interviewer time, transcription, travel to facilities
Analyze data and disseminate findings
Biostatistician time, conference travel, publication fees
ACTIVITY
BUDGET LINE
The Alignment Rule: Every technical activity needs a budget linety.
Goal: 100% of activities funded · 0% of budget lines orphaned

## Slide 12: Budget Categories in Typical Health Research Grants
Category | Examples
Personnel | PI, Co-I, Research assistants
Fringe benefits | Insurance, benefits
Equipment | Servers, laboratory devices
Supplies | Printing, consumables
Travel | Field visits, conferences
Subcontracts | Partner institution
Other direct costs | Ethics review, dissemination
Indirect costs | Institutional overhead

## Slide 13
Practice: Building a budget line from a study protocol activity
Field | Worked Example
Activity | Conduct qualitative interviews with 40 health facility managers across 3 regions
Cost driver | Interviewer days, transcription per interview, travel days, participant incentives
Quantities | 3 regions × 1 interviewer × 5 days; 40 interviews total
Unit cost | Interviewer $200/day; transcription $35/interview; travel $150/day; incentive $15/participant
Line total | $3,000 + $1,400 + $2,250 + $600 = $7,250
Budget line | "Qualitative Data Collection" — direct cost, Aim 2
Try it: pick one activity from your own study protocol and build its budget line the same way — driver, quantity, unit cost, total.
12

## Slide 14: Practical Demonstration: Costing Personnel Time
Interactive calculation:
Example:
  Principal Investigator: 15% FTE
  Co-Investigator: 10% FTE
  Project Coordinator: 50% FTE
  Data Collector: 40 days
Let us do:
  Effort calculation
  Annual salary conversion
  Total personnel cost

## Slide 15: Budget Review Checklist
Questions reviewers ask:
  Is the budget complete?
  Is it realistic?
  Is it allowable?
  Are indirect costs correct?
  Is cost sharing documented?
  Does each activity have funding?
  Does funding support the proposed outputs?

## Slide 16: Writing a budget narrative that survives review
State the cost driver: unit, quantity, and rate for every line
Link explicitly to the activity and work plan reference number
Use realistic, sourced assumptions — not round-number guesses
Show the math: quantity × unit cost = line total, every time
Flag any cost-share, in-kind value, or shared/indirect basis used

## Slide 17
Red flags: signs your budget and workplan have drifted apart
Orphan activities
A technical activity in the workplan has no corresponding budget line to fund it.
Orphan budget lines
A cost is budgeted but no activity in the workplan explains why it's needed.
Timing mismatch
Costs are budgeted in a period before or after the activity they fund occurs.
Vague cost drivers
Line items with no unit, quantity, or basis — impossible to verify or justify.
A budget passes review only when a technical lead and a finance lead can each independently trace every line to an activity and every activity to a line.
11

## Slide 18: Group Activity 1: Costing a Maternal & Child Health Systems Research Project
Identify the budget categories the study will require.
Estimate direct costs for the study's major activities.
Identify indirect costs and how they should be applied.
Determine what could realistically be offered as cost-share.
Find what's missing — activities or requirements implied by the concept note but not yet accounted for in a budget.

## Slide 19: Grant Execution & Post-Award Management
Mirkuzie Woldie (MD, MPH)
Professor of Health Systems Management

## Slide 20
By the end of this session, you will be able to:
Plan rapid post-award initiation
Assemble your team, engage stakeholders, and set up M&E in the critical first weeks.
Manage reporting milestones
Track every technical, financial, and M&E deadline the award requires.
Maintain transparent donor communication
Flag issues early and keep funders informed before they have to ask.
Navigate consortium formation
Define roles, governance, and agreements across partner institutions.
Apply negotiation & conflict management
Handle scope and budget changes without damaging the relationship.
2

## Slide 21
The first 90 days set the trajectory for the entire award
Team Assembly
The right people, in place fast
+
Stakeholder Engagement
Buy-in from donor to community
+
M&E Setup
Systems ready before data flows
=
Fast, Compliant
Start
Slow start
Delayed hiring and setup burns months of the award period
Rushed start
Skipping stakeholder buy-in creates resistance and rework later
Right start
Team, engagement, and M&E built in parallel from day one
4

## Slide 22: Post-Award Start-Up Checklist
People
Recruit key staff
Assign project roles
Clarify decision-making authority
Systems
Financial tracking system
Procurement processes
Reporting calendar
Stakeholders
Donor briefing
Government engagement
Partner kick-off meeting
Monitoring
Baseline assessment
Indicator definitions
Data collection tools

## Slide 23: Stakeholder Analysis Matrix
Stakeholder Name | Contact Person Phone, Email, Website, Address | Impact How much does the project impact them? (Low, Medium, High) | Influence How much influence do they have over the project? (Low, Medium, High) | What is important to the stakeholder? | How could the stakeholder contribute to the project? | How could the stakeholder block the project? | Strategy for engaging the stakeholder
EXAMPLE Nurses & Midwives Union | Abebe Demeke abebedemeke@stakeholder.org 0999 888 777 Addis Ababa, Ethiopia | High | High | Maintaining working conditions for nurses | Agree for union members to implement the new reforms | Going on strike | Monthly round-table discussions

## Slide 24: Power – Interest Matrix

## Slide 25
Stakeholder engagement: who to bring in during initiation
Each stakeholder group needs a distinct, early conversation — not a single blanket announcement.
Sequence matters: IRB and government registration often gate everything else — start them immediately.
Donor / Funder
Confirm reporting formats, deadlines, and communication norms
Partner Institutions
Clarify roles, deliverables, and subaward terms in writing
Government / MOH /RHBs? / health facilities
Register the study and align with national health priorities
Community & Participants
Share study purpose, consent process, and expected benefits
IRB / Ethics Board
Secure approvals before any data collection begins
6

## Slide 26: Establishing M&E Systems Early
Indicators
Targets
Data collection tools
Reporting templates
Roles and responsibilities
Learning agenda
Theory of change (ToC)

## Slide 27
The 0–30–60–90 days post-award plan
Day 0–7
Launch
Kickoff meeting held
Core team confirmed
Subawards initiated
Day 8–30
Set Up
Staff onboarded
IRB/ethics submitted
Finance & M&E systems live
Day 31–60
Engage
Baseline data collection starts
Partner agreements signed
First stakeholder update sent
Day 61–90
Stabilize
M&E dashboard live
First progress report drafted
Risk/issues log reviewed
Session 10 · Grant Execution & Post-Award Management
8

## Slide 28: Managing Reporting Milestones
Typical reporting requirements:
Inception report
Progress reports
Financial reports
Annual reports
Final reports
Notes: Demonstrate a reporting tracker:
| Deliverable | Due Date | Responsible Person | Status |

## Slide 29
Building a reporting calendar: mapping deliverables across the year
Q1
Q2
Q3
Q4
Financial Report
M&E / Indicator Report
Technical Progress Report
Annual Report
10

## Slide 30: Transparent donor communication: no surprises, ever
Flag problems as soon as they're identified — not at the next scheduled report
Document communications in writing, even after verbal conversations
Share both good news and bad news with the same promptness
Come to donors with a proposed solution, not just a problem
Watch for: the annual report disclosing a budget shortfall, a delay, or a partner issue the team already knew about internally.

## Slide 31: Managing Change During Implementation
Explain three common changes:
Scope Changes
New activities
Expanded objectives
Budget Changes
Reallocation between lines
Cost escalation
Timeline Changes
Delays
Extensions
Notes: Introduce:
Golden Rule: Never assume approval. Obtain donor authorization when required.

## Slide 32: Consortium Formation and Management
Why Form Consortia?
Technical expertise
Geographic reach
Credibility
Shared resources
Common Members
Universities
NGOs
Government agencies
International collaborators

## Slide 33: Consortium Goverance
Key elements:
Lead institution
Sub-awards
Work package leads
Communication protocols
Reporting responsibilities
Important agreements:
Roles and responsibilities
Budget allocation
Data ownership
Publication policy
Conflict resolution procedures

## Slide 34: Consortium formation: structuring multi-partner awards
 | Lead / Prime Recipient | Sub-Recipient / Partner
Legal responsibility | Holds the prime award; accountable to the donor | Accountable to the lead via subaward agreement
Financial flow | Receives funds directly; disburses to partners | Receives and reports funds through the lead
Reporting obligation | Consolidates and submits all reports to donor | Submits inputs to the lead on an agreed schedule
Decision authority | Final say on budget and scope changes | Consulted per the governance structure
Governance essentials
Subaward agreements
Scope, budget, and compliance terms in writing
Governance structure
A steering committee with clear decision rights
Role matrix
Document who does what to prevent overlap and gaps

## Slide 35: Red flags: signs a consortium is heading for trouble
Undefined roles: No written matrix of who owns which deliverable — overlaps and gaps surface mid-project.
Unequal capacity: One partner can't meet financial or reporting requirements, and no one has a support plan.
Financial mismatches: Subawardee expenditure reports don't reconcile with the lead's consolidated financials.
Silent disagreement: Partners raise concerns informally, but nothing reaches the governance committee.

## Slide 36: Core Skills for Grant management: negotiation and conflict management
When negotiation is needed
  Budget reallocation requests exceeding donor thresholds
  Scope adjustments due to context changes (security, logistics, policy)
  Timeline extensions and no-cost extensions
  Disagreements among consortium partners over resources or credit
Core skills to bring into the room
Active listening
Understand underlying interests, not just stated positions
Principled negotiation
Separate people from the problem; focus on shared interests
Structured escalation
Know when and how to involve leadership or a mediator
Written follow-up
Document agreements to prevent future disputes

## Slide 37
The escalation ladder: resolve at the lowest effective level
1
Direct conversation
Resolve informally, in real time, between the parties involved
2
Project / program manager mediation
Bring in a neutral internal party to help find common ground
3
Institutional leadership review
Escalate to the PI or institutional authority for a binding decision
4
Donor or external mediation
Involve the funder only when internal options are exhausted
15

## Slide 38: Conflict Management in Research Partnerships
Common Sources of Conflict
Delayed deliverables
Unequal workload
Budget disputes
Authorship issues
Data ownership concerns
Conflict resolution model:
Recognize → Understand → Discuss → Negotiate → Resolve → Document

## Slide 39: Risk Management During Grant Execution
Possible sources of risk
Staff turnover
Procurement delays
Political instability
Data quality issues
Currency fluctuations
Identify
Risk
Likelihood
Impact
Mitigation

## Slide 40: Success Factors for Effective Grant Management
Strong leadership
Clear governance
Early M&E setup
Transparent donor communication
Effective consortium management
Strong negotiation skills
Proactive risk management

## Slide 41: Group Activity 2: Managing Change Mid-Study: The Jimma Case Update
Read the situation update as a group, then work through four steps that mirror the core skills from Session 10:
  Take on a role and negotiate an internal resolution to three open questions.
  Draft a short, proactive donor communication.
  Decide where this issue sits on the escalation ladder — and defend it.
  Debrief: What would you have done differently earlier in the study?